## Product Backlog- Team Euler
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us:101 | Customer must create his Account | Very Simple | L | Functional
2 | 2 |  | M | Us:102 | Customer must login into the application | Complex | M | Functional
3 | 3 |  | M | Us:103 | Customer can check for available flights (check all flights b/w given route) | Very Simple | L | Technical
4 | 4 |  | M | Us:104 | Customer can make a booking (Id genrated automatically) | Very Simple | L | Technical
5 | 5 |  | M | Us:105 | Customer can view the booking made | Very Simple | L | Technical
6 | 6 |  | M | Us:106 | Customer can cancel or modify a booking | Very Simple | L | Technical
7 | 7 |  | S | Us:107 | Customer should have 12-digit Unique Identification number | Average | L | Technical
8 | 8 |  | S | Us:108 | Customer can change their credentials (Forgot Password) | Average | L | Technical
9 | 9 |  | C | Us:109 | Customer can delete account | Very Simple | L | Technical
10 | 10 |  | M | Us: 110 | Admin can login into the application | Complex | H | Functional
11 | 11 |  | M | Us: 111 | Admin can add flights, schedule flights | Complex | L | Technical
12 | 12 |  | M | Us: 112 | Admin can view flights, schedule flights | Average | L | Technical
13 | 13 |  | M | Us: 113 | Admin can cancel or modify flight, schedule flights and route details | Average | L | Technical
14 | 14 |  | S | Us: 114 | Admin can delete the account of Customer | Very Simple | L | Technical
15 | 15 |  | S | Us: 115 | Admin can view and validate the Customer | Very Simple | L | Technical
16 | 16 |  | S | Us: 116 | Admin can update Airport Details | Very Simple | L | Technical
17 | 17 |  | W | Us: 117 | The application does not cover boarding pass generation and seating plans. | Very Simple | L | Non-Functional
18 | 18 |  | W | Us: 118 | Third party applications like email & sms integrations. | Very Simple | L | Non-Functional
19 | 19 |  | W | Us: 119 | Payments are not yet accepted by the application | Very Simple | L | Non-Functional
20 | 20 |  | W | Us: 120 | Customers are not able to do Web Check-In | Very Simple | L | Non-Functional
21 | 21 |  | W | Us: 121 | Customers cannot check their Flight Status | Very Simple | L | Non-Functional
22 | 22 |  | M | Us: 122 | Admin can add Airport | Simple | L | Technical
23 | 23 |  | M | Us: 123 | Authentication of the User(Valid/Invalid User) | Average | L | Functional
24 | 24 |  | M | Us: 124 | Admin can add/modify Customer and Passenger | Average | M | Technical
25 | 25 |  | C | Us: 125 | Session Timeout(if no activity) | Complex | M | Functional
26 | 26 |  | W | Us: 126 | Chatbot | Average | H | Non-Functional
27 | 27 |  | S | Us: 127 | User can Logout | Average | L | Functional
28 | 28 |  | C | Us: 128 | Asking for choice again on wrong selection | Average | L | Technical
29 | 29 |  | C | Us: 129 | Ticket options as business, economy, first class. | Average | L | Technical
30 | 30 |  | M | Us: 130 | Admin can schedule the flights | Average | L | Technical

## Sprint Backlog- Team Euler
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
P:01 | Us:101 | 1 | POJO class for User | Vaibhav | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:02 | Us:122 | 1 | POJO class for Airport | Vaibhav | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:03 | Us:104 | 1 | Create POJO class for Booking | Shaivi | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:04 | Us:124 | 1 | Create POJO class for Passenger | Shaivi | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:05 | Us:111 | 1 | Create POJO for Schedule Flights | Shivani | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:06 | Us: 130 | 1 | Create POJO for Schedule | Shivani | 2020-04-25 21:42 | 2020-04-26 12:00 | 2020-04-27 13:00 | Done
P:07 | Us:111 | 1 | Create POJO for Flights details | Sanchit | 2020-04-25 21:42 | 2020-04-26 12:00 | Nil | Done
P:08 | Us:101 | 1 | Make Database and apply annotation and all required validation in POJO classe of Users | Shivani | 2020-04-27 13:35 | 2020-04-27 15:00 | Nil | Done
P:09 | Us:130 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Schedule | Vaibhav | 2020-04-27 13:35 | 2020-04-27 15:00 | Nil | Done
P:10 | Us:111 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Flight | Vaibhav | 2020-04-27 13:35 | 2020-04-27 15:00 | Nil | Done
P:11 | Us: 122 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Airport | Sanchit | 2020-04-27 13:35 | 2020-04-27 15:00 | Nil | Done
P:12 | Us: 111 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Schedule Flight | Sanchit | 2020-04-27 13:35 | 2020-04-27 15:00 | Nil | Done
P:13 | Us:101 | 1 | Dao Implementation | Vaibhav | 2020-04-27 18:56 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 2 | Service Implementation | Vaibhav | 2020-04-27 18:56 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 3 | Controller methods | Vaibhav | 2020-04-27 18:56 | 2020-04-28 23:00 | 2020-04-29 18:00 | Done
P:14 | Us:124 | 1 | Dao Implementation | Vaibhav | 2020-04-27 18:56 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 2 | Service Implementation | Vaibhav | 2020-04-27 18:56 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 3 | Controller methods | Vaibhav | 2020-04-27 18:56 | 2020-04-28 23:00 | 2020-04-29 18:00 | Done
P:15 | Us:122 | 1 | Dao Implementation | Shaivi | 2020-04-27 18:57 | 2020-04-28 15:00 | Nil | Done
|  | 2 | Service Implementation | Shaivi | 2020-04-27 18:57 | 2020-04-28 15:00 | Nil | Done
|  | 3 | Controller methods | Shaivi | 2020-04-27 18:57 | 2020-04-28 23:00 |  | Done
P:16 | Us:111 | 1 | Dao Implementation | Shaivi | 2020-04-27 18:57 | 2020-04-28 15:00 | Nil | Done
|  | 2 | Service Implementation | Shaivi | 2020-04-27 18:57 | 2020-04-28 15:00 | Nil | Done
|  | 3 | Controller methods | Shaivi | 2020-04-27 18:57 | 2020-04-28 23:00 |  | Done
P:18 | Us:130 | 1 | Dao Implementation | Shivani | 2020-04-27 19:02 | 2020-04-28 15:00 | Nil | Done
|  | 2 | Service Implementation | Shivani | 2020-04-27 19:02 | 2020-04-28 15:00 | Nil | Done
|  | 3 | Controller methods | Shivani | 2020-04-27 19:02 | 2020-04-28 23:00 |  | Done
P:18 | Us:111 | 1 | Dao Implementation | Shivani | 2020-04-27 19:02 | 2020-04-28 15:00 | Nil | Done
|  | 2 | Service Implementation | Shivani | 2020-04-27 19:02 | 2020-04-28 15:00 | Nil | Done
|  | 3 | Controller methods | Shivani | 2020-04-27 19:02 | 2020-04-28 23:00 |  | Done
P:18 | Us:104 | 1 | Dao Implementation | Sanchit | 2020-04-27 18:57 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 2 | Service Implementation | Sanchit | 2020-04-27 18:57 | 2020-04-28 15:00 | 2020-04-28 18:00 | Done
|  | 3 | Controller methods | Sanchit | 2020-04-27 18:57 | 2020-04-28 21:00 |  | Done
P:18 | Us:102 | 1 | Dao Implementation | Sanchit | 2020-04-27 18:57 | 2020-04-28 15:00 |  | Done |  | will look after the completiton of front end as need to study about Spring Security. Its Front End is Completed looking for the backedn
|  | 2 | Service Implementation | Sanchit | 2020-04-27 18:57 | 2020-04-28 15:00 |  | Done |  | will look after the completiton of front end as need to study about Spring Security. Its Front End is Completed looking for the backedn
|  | 3 | Controller methods | Sanchit | 2020-04-27 18:57 | 2020-04-29 23:00 |  | Done |  | will look after the completiton of front end as need to study about Spring Security. Its Front End is Completed looking for the backedn
P:20 | Us:122 | 1 | Service Implementation and Interface make them seprate | Shaivi | 2020-04-29 | 2020-04-29 23:59 |  | Done
P:21 | Us:111 | 1 | Service Implementation and Interface make them seprate | Shaivi | 2020-04-29 | 2020-04-29 23:59 |  | Done
P:22 | Us:130 | 1 | Service Implementation and Interface make them seprate | Shivani | 2020-04-29 | 2020-04-29 23:59 |  | Done
P:23 | Us:104 | 1 | Service Implementation and Interface make them seprate | Sanchit | 2020-04-29 | 2020-04-29 23:59 |  | Done
P:24 | Us:124 | 1 | Service Implementation and Interface make them seprate | Vaibhav | 2020-04-29 | 2020-04-29 23:59 |  | Done
P:20 | Us: 102 | 1 | make front end for Welcome Customer | Vaibhav | 2020-04-30 20:07 | 2020-05-01 12:00 |  | Done |  | Please refer page 16 of case study for design
P:21 | Us:111 | 1 | make frond end for admin | Vaibhav | 2020-04-30 20:07 | 2020-05-01 12:00 |  | Done |  | Please refer page 19 of case study for design
P:22 | Us: 113 | 1 | make front end for update flight | Shaivi | 2020-04-30 20:16 | 2020-05-01 12:00 |  | Done |  | Please refer page 20 of case study for design
P:23 | Us: 105 | 1 | front end for Your booking | Shaivi | 2020-04-30 20:16 | 2020-05-01 12:00 |  | Done |  | Please refer page 15 of case study for design
P:24 | Us: 110 | 1 | make front end for Welcome Admin | Shivani | 2020-04-30 20:17 | 2020-05-01 12:00 |  | Done |  | Please refer page 17 of case study for design
P:25 | Us:104 | 1 | front end for booking confirmend message | Shivani | 2020-04-30 20:17 | 2020-05-01 12:00 |  | Done |  | Please refer page 12 of case study for design
P:26 | Us:104 | 1 | front end for Booking Details | Sanchit | 2020-04-30 20:24 | 2020-05-01 12:00 |  | Done |  | Please refer page 11 of case study for design
P:27 | Us:113 | 1 | front end for update flight enter details | Sanchit | 2020-04-30 20:24 | 2020-05-01 12:00 |  | Done |  | Please refer page 21 of case study for design
P:19 | Us:101 | 1 | Controller methods | Sanchit | 2020-05-02 12:00 |  |  | Done |  | will look after the completiton of front end as need to study about Spring Security. Its Front End is Completed looking for the backedn
|  | 2 | Service Implementation | Sanchit | 2020-05-02 12:00 |  |  | Done |  | will look after the completiton of front end as need to study about Spring Security. Its Front End is Completed looking for the backedn
P:28 | Us:130 | 1 | Add Schedule Flight Front End | Shivani | 2020-05-04 11:45 | 2020-05-05 18:00 |  | Done |  | Please refer page 23 of case study for design
|  | 2 | Delete Schedule Flight Front End | Shivani | 2020-05-04 11:45 | 2020-05-05 18:00 |  | Done |  | Please refer page 24 of case study for design
|  | 3 | Modify Schedule Flight Front End | Shivani | 2020-05-04 11:45 | 2020-05-05 18:00 |  | Done |  | Please refer page 26 of case study for design
|  | 4 | Search Schedule Flight Front End | Shivani | 2020-05-04 11:45 | 2020-05-05 18:00 |  | Done |  | Please refer page 27 of case study for design
P:29 | Us:111 | 1 | Add Flight Front End | Shaivi | 2020-05-04 12:03 | 2020-05-05 18:00 |  | Done |  | Please refer page 19 of case study for design
|  | 2 | Delete Flight Front End | Shaivi | 2020-05-04 12:03 | 2020-05-05 18:00 |  | Done |  | Please refer page 20 of case study for design
|  | 3 | Modify Flight Front End | Shaivi | 2020-05-04 12:03 | 2020-05-05 18:00 |  | Done |  | Please refer page 20 of case study for design
|  | 4 | Search Flight Front End | Shaivi | 2020-05-04 12:03 | 2020-05-05 18:00 |  | Done |  | Please refer page 21 of case study for design
P:30 | Us:101 | 1 | Add User Front End | Vaibhav | 2020-05-04 12:11 | 2020-05-05 18:00 |  | Done
|  | 2 | Delete User Front End | Vaibhav | 2020-05-04 12:11 | 2020-05-05 18:00 |  | Done
|  | 3 | Modify User Front End | Vaibhav | 2020-05-04 12:11 | 2020-05-05 18:00 |  | Done
P:31 | Us:104 | 1 | Add Booking Front End | Sanchit | 2020-05-04 12:14 | 2020-05-05 18:00 |  | Done
|  | 2 | Delete Booking Front End | Sanchit | 2020-05-04 12:14 | 2020-05-05 18:00 |  | Done
|  | 3 | Modify Booking Front End | Sanchit | 2020-05-04 12:14 | 2020-05-05 18:00 |  | Done
|  | 4 | Search Booking Front End | Sanchit | 2020-05-04 12:14 | 2020-05-05 18:00 |  | Done
P:32 | Us:130 | 1 | Validations | Shivani | 2020-05-06 | 2020-05-07 |  | Done
|  | 2 | Exception Handling | Shivani | 2020-05-06 | 2020-05-07 |  | Done
|  | 3 | Http Status Code | Shivani | 2020-05-06 | 2020-05-07 |  | Done
P:33 | Us:111 | 1 | Validations | Shaivi | 2020-05-06 | 2020-05-07 |  | Done
|  | 2 | Exception Handling | Shaivi | 2020-05-06 | 2020-05-07 |  | Done
|  | 3 | Http Status Code | Shaivi | 2020-05-06 | 2020-05-07 |  | Done
P:34 | Us:101 | 1 | Validations | Vaibhav | 2020-05-06 | 2020-05-07 |  | Done
|  | 2 | Exception Handling | Vaibhav | 2020-05-06 | 2020-05-07 |  | Done
|  | 3 | Http Status Code | Vaibhav | 2020-05-06 | 2020-05-07 |  | Done
P:35 | Us:104 | 1 | Validations | Sanchit | 2020-05-06 | 2020-05-07 |  | Done
|  | 2 | Exception Handling | Sanchit | 2020-05-06 | 2020-05-07 |  | Done
|  | 3 | Http Status Code | Sanchit | 2020-05-06 | 2020-05-07 |  | Done
P:36 | Us:130 | 1 | Angular UI to backend connectivity | Shivani | 2020-05-08 12:49 | 2020-05-08 18:00 |  | Done
P:37 | Us:111 | 1 | Angular UI to backend connectivity | Shaivi | 2020-05-08 12:49 | 2020-05-08 18:00 |  | Done
P:38 | Us:101 | 1 | Angular UI to backend connectivity | Vaibhav | 2020-05-08 12:49 | 2020-05-08 18:00 |  | Done
P:39 | Us:104 | 1 | Angular UI to backend connectivity | Sanchit | 2020-05-08 12:49 | 2020-05-08 18:00 |  | Done
P:40 | Us:101 | 2 | Home Component | Sanchit | 2020-05-08 12:49 | 2020-05-08 18:00 |  | Done
P:41 | Us:130 | 1 | Connect angular component of ScheduleFlight with other components | Shivani | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 2 | Angular Componet with angular Validations | Shivani | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
P:42 | Us:111 | 1 | Connect angular component of Flight and Airport with other components | Shaivi | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 2 | Angular Componet with angular Validations | Shaivi | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
P:43 | Us:101 | 1 | Connect angular component of User with other components | Vaibhav | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 2 | Angular Componet with angular Validations | Vaibhav | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
P:44 | Us:104 | 1 | Connect angular component of Login/SignUp and Booking with other components | Sanchit | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 2 | Angular Componet with angular Validations | Sanchit | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
P:45 | Us:101 | 1 | Adding Login Functionality in Angular | Sanchit | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 2 | Adding Logout Functionality in Angular | Sanchit | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
|  | 3 | Adding SignUp Functionality in Angular | Sanchit | 2020-05-09 12:00 | 2020-05-09 21:00 |  | Done
P:46 | - | 1 | Integartion of all Front End Angular Part | Sanchit | 2020-05-10 12:00 | 2020-05-10 18:00 |  | Done
|  | 2 | Adding Functionallity of Login/Logout | Sanchit | 2020-05-10 12:00 | 2020-05-11 23:55 |  | Done
|  | 3 | Testing the project flow of Angular | Sanchit | 2020-05-10 18:00 | 2020-05-10 21:00 |  | Done
P:47 | Us:130 | 1 | JUnit Testing using Mockito and Front End make attractive | Shivani | 2020-05-11 12:00 | 2020-05-11 18:00 |  | Done
P:48 | Us:111 | 1 | JUnit Testing using Mockito and Front End make attractive | Shaivi | 2020-05-11 12:00 | 2020-05-11 18:00 |  | Done
P:49 | Us:101 | 1 | JUnit Testing using Mockito and Front End make attractive | Vaibhav | 2020-05-11 12:00 | 2020-05-11 18:00 |  | Done
P:50 | Us:104 | 1 | JUnit Testing using Mockito and Front End make attractive | Sanchit | 2020-05-11 12:00 | 2020-05-11 18:00 |  | Done
P:51 | Us:130 | 1 | Implementation of Microservices | Shivani | 2020-05-12 | 2020-05-13 12:00 |  | Done
|  | 2 | Testing the Integration of Backend and Frontend | Shivani | 2020-05-12 | 2020-05-12 |  | Done
P:52 | Us:111 | 1 | Fixing Bug for Airport and Flight Backend | Shaivi | 2020-05-12 | 2020-05-13 12:00 |  | Done
|  | 2 | Implementation of Microservices | Shaivi | 2020-05-12 | 2020-05-12 |  | Done
P:53 | Us:101 | 1 | Implementation of Microservices | Vaibhav | 2020-05-12 | 2020-05-13 12:00 |  | Done
|  | 2 | Testing the Integration of Backend and Frontend | Vaibhav | 2020-05-12 | 2020-05-12 |  | Done
P:54 | 101 | 1 | Implementing Login/Logout module | Sanchit | 2020-05-12 | 2020-05-12 |  | Done
|  | 2 | Implementation of Microservices | Sanchit | 2020-05-12 | 2020-05-13 12:00 |  | Done
|  | 3 | Testing the Integration of Backend and Frontend | Sanchit | 2020-05-12 | 2020-05-12 |  | Done
|  | 4 | Integration of the Test Cases and Backedn of whole project | Sanchit | 2020-05-12 | 2020-05-12 |  | Done